Lakk. /ቁጥር/Ref.: ____/ ____/____

Guyyaa/ቀን/Date: ____/ ____/____

- To: All Case Teams

- OPD

- Pediatrics

- EOPD

- Maternity

- NICU

- Surgical Ward

- ICU

- Medical Ward

- Operating Room (OR)

- Laboratory

- Pharmacy

- Administrative Office

- From: Ibrahim Tahir, IPC Officer
Subject: Feedback on IPC Monitoring – 2nd Quarter 2017 E.C.

Dear Team Leaders and Members,

Following the comprehensive IPC monitoring assessment conducted on December 28, 2017 E.C at Deder General Hospital, this letter provides consolidated feedback to all case teams regarding Infection Prevention and Control (IPC) practices during the first quarter.

While we commend the hospital for achieving an overall IPC compliance rate of 81% and maintaining strong structural systems, several operational gaps at the point of care require urgent attention to ensure full protection of patients and staff.

Key Observed Gaps:

- Inconsistent PPE usage in many departments (e.g., OPD, ICU, OR, Lab)

- Hand hygiene supplies unavailable at many care points

- Irregular cleaning and disinfection of high-touch surfaces and equipment

- Poorly managed waste and sharps containers

- Lack of isolation corners, especially in critical care units

- Open linen storage and weak specimen spill protocols

Feedback Summary Table (2nd Quarter 2017 E.C):

| Case Team | Key IPC Gaps Identified | Recommendations | Responsible Body | Timeline |
| --- | --- | --- | --- | --- |
| OPD, Pediatrics, EOPD | - Incomplete PPE use- Missing hand hygiene supplies- Patient transport not controlled | - Refresher PPE training- Restock hygiene materials- Assign transport focal persons | IPC Committee, Unit Heads, Pharmacy | Weeks 1–2 |
| Maternity Ward | - Low PPE use- Soap/rub missing at delivery beds- Unclean equipment- Overfilled sharps bins | - PPE training- Ensure hygiene materials- Cleaning logs- Covered linen bins | Maternity Lead, Environmental Health, Cleaners | Immediate – 1 week |
| NICU | - PPE inconsistency- Hand rub stations empty- No isolation corner- Soiled linen bins | - Reinforce PPE use- Constant hygiene supply- Establish isolation corner- Cleaning logs | NICU Lead, IPC Team, Facility Mgmt | Week 1–Month 1 |
| Surgical Ward | - Improper PPE during wound care- Missed hand hygiene- Unclean instruments- Sharps bins overfilled | - PPE refreshers- Daily cleaning checks- Monitor sharp bins- Covered linen containers | Ward Head, IPC, Cleaners, Environmental Health | Immediate – Week 1 |
| ICU | - Incomplete PPE during suction/care- Limited rub/soap access- No isolation area- Poor waste handling | - Reinforce PPE with checklists- Ensure 24/7 hand hygiene supply- Create isolation zone- Improve waste segregation | ICU Head, IPC Team, Cleaning, Facility Management | Week 1–2 |
| Medical Ward | - Low hand hygiene compliance- PPE not used for all patients- High-touch surfaces missed during cleaning | - Audit and train staff on WHO 5 Moments- Display PPE reminders- Cleaning checklist updates | Ward Head, IPC, Environmental Health | Week 1–2 |
| Operating Room | - Inconsistent mask/gown use pre-procedure- Reusable instruments poorly disinfected- Overflowing sharps | - PPE enforcement protocols- Audit instrument reprocessing- Immediate sharp disposal | OR Lead, IPC Team, Sterile Processing | Within 1 week |
| Laboratory | - Lab coat/eye protection missing- Missed hygiene after glove removal- No spill protocol | - PPE and hand hygiene refreshers- Develop & train on spill SOP- Monitor bench disinfection | Lab Supervisor, IPC Team, Environmental Health | Week 1–2 |
| Pharmacy | - Poor PPE use- Unclean counters- No hazardous waste bins- Poor med storage near water/sinks | - PPE refreshers- Procure waste bins- Cleaning logs- Reorganize meds storage | Pharmacy Head, IPC, Procurement | Week 1–2 |
| Admin Office | - Poor hand hygiene practices- Shared surfaces not cleaned- Lack of IPC signage or protocols | - Awareness training- Provide desk sanitizer/rub- Place visual IPC reminders | Admin Head, IPC Team | Week 1–2 |

Recommendations and Required Actions:

- Refresher trainings on PPE use and hand hygiene for all departments.

- Ensure continuous supply and proper placement of alcohol-based hand rub and soap.

- Enforce daily environmental cleaning logs and supervisory checks.

- Monitor and promptly dispose of sharps containers.

- Distribute hazardous/chemical waste bins where needed.

- Set up designated isolation areas, even temporary, in high-risk units.

- Develop and disseminate spill management SOPs, especially for labs and wards.

- Assign IPC focal points in every department.

- Participate in monthly IPC audits and act on corrective measures.

Conclusion:

We acknowledge the significant progress made, but IPC is a continuous effort. With collaboration, strict adherence, and proactive management, we can protect our staff and patients from preventable infections.

Please acknowledge this feedback letter and submit your unit-specific action plan within two weeks to the IPC Office.

Sincerely,
Ibrahim Tahir
Infection Prevention and Control Officer