DEDER GENERAL HOSPITAL

IPC Program

Outbreak Preparedness and Response Plan

July, 2016 EC

Deder, Ethiopia

TABLE OF CONTENTS

Introduction	1

Purpose	1

Objectives	2

Key Components & Activities	2

Roles of the Outbreak Response Committee (ORC)	5

Review and Update	5

# Introduction

Infectious disease outbreaks pose significant risks to patient safety, healthcare worker well-being, and health system functionality. Healthcare facilities, especially general hospitals like Deder, must maintain a constant state of readiness to detect and respond to outbreaks such as COVID-19, tuberculosis (TB), measles, cholera, and other high-impact pathogens.

Preparedness is a critical part of infection prevention and control (IPC) and requires proactive planning, trained personnel, clear protocols, and strong coordination mechanisms. This Outbreak Preparedness and Response Plan outlines how Deder General Hospital will detect, respond to, and recover from potential infectious disease outbreaks while ensuring patient care continuity and minimizing transmission risks.

# Purpose

To ensure that Deder General Hospital is fully prepared to detect, contain, and respond to infectious disease outbreaks in a timely, coordinated, and effective manner. This plan aims to minimize the spread of disease within the facility, protect patients and staff, and maintain continuity of essential services.

# Objectives

- Establish early warning systems for outbreak detection.

- Define clear outbreak response roles and escalation protocols.

- Ensure readiness of triage, isolation, and referral systems.

- Maintain sufficient IPC supplies and trained staff for emergencies.

- Facilitate coordination with public health authorities for reporting and support.

- Conduct simulation exercises and periodic reviews of outbreak protocols.

# Key Components & Activities

| Component | Planned Activities | Frequency / Timeline | Responsible Units |
| --- | --- | --- | --- |
| A. Surveillance & Early Detection | - Implement daily syndromic surveillance in high-risk wards (e.g., Emergency, Maternity, TB clinic). - Use WHO/MOH case definitions. - Activate Outbreak Task Force upon threshold breach. | Continuous | IPC Team, M&E Unit, Department Heads |
| B. Rapid Response Activation | - Notify Outbreak Response Committee within 24 hours. - Classify outbreak risk (internal cluster vs. external community). - Initiate outbreak investigation and contact tracing. | Within 24 hrs of case cluster | Medical Director, IPC Focal |
| C. Triage & Isolation Protocols | - Set up respiratory triage stations at all main entry points. - Designate and equip isolation rooms. - Train frontline staff in emergency triage. | Quarterly drills Real-time during outbreaks | Emergency Dept., IPC Team, Facility Management |
| D. Supplies & Logistics | - Maintain buffer stock of PPE, disinfectants, specimen kits. - Activate emergency procurement protocols. - Monitor and log PPE usage daily during outbreak. | Monthly stock reviews Emergency activation | Pharmacy, Procurement, IPC Store Manager |
| E. Communication & Coordination | - Assign spokesperson for internal/external updates. - Use visual alerts, SMS, and staff briefings. - Submit reports to Woreda/Zonal Health Office. | Weekly (during outbreak) | IPC Focal, Hospital Communications Officer |
| F. Staff Protection & Support | - Enforce PPE compliance and exposure monitoring. - Offer PEP/testing for exposed staff. - Modify duty rosters to minimize cross-unit transmission. | Daily monitoring | HR Unit, Occupational Health, IPC Committee |
| G. Training & Simulation Drills | - Conduct biannual simulation drills (e.g., COVID-19, TB, cholera). - Refresh triage, isolation, reporting procedures. | Biannually | IPC Unit, Emergency Preparedness Team |
| H. Post-Outbreak Review & Learning | - Debrief within 1 week of outbreak resolution. - Analyze gaps and update SOPs. - Submit report to hospital management. | Post-outbreak | ORC, M&E Officer, IPC Focal |

Preparedness Resources Checklist

| Item | Target Level |
| --- | --- |
| Functional isolation rooms | ≥2 per facility |
| Triage stations | All outpatient and emergency entry points |
| N95/Respirators | 2-week stock for all high-risk units |
| Outbreak SOPs | Posted in all departments |
| Emergency contact list | Updated quarterly |
| Simulation drill reports | 2 per year minimum |
| Exposure registry | Continuously updated |

# Roles of the Outbreak Response Committee (ORC)

- Activate response plan upon outbreak confirmation.

- Lead coordination and reporting to external authorities.

- Ensure compliance with IPC measures hospital-wide.

- Document all actions and lessons learned.

Refer to the TOR in Section 13.1 for full committee structure and responsibilities.

# Review and Update

This outbreak preparedness and response plan shall be reviewed:

- Annually during the IPC workplan review.

- After every outbreak with documented lessons learned integrated into SOPs and drills