Lakk. /ቁጥር/Ref.: ____/ ____/____

Guyyaa/ቀን/Date: ____/ ____/____

- To: All Case Teams

- OPD

- Pediatrics

- EOPD

- Maternity

- NICU

- Surgical War

- Laboratory

- Pharmacy

- From: Ibrahim Tahir, IPC Officer

Subject: Feedback on IPC Monitoring – 1st Quarter 2017 E.C.

Dear Team Leaders and Members,

Following the comprehensive IPC monitoring assessment conducted on September 28, 2017 E.C across Deder General Hospital, I am writing to provide consolidated feedback to all case teams regarding the status of Infection Prevention and Control practices during the first quarter of 2017 E.C.

Our findings indicate that while the hospital has established strong IPC systems and policies, significant gaps remain in consistent implementation at the point of care. Key areas requiring urgent attention include:

- Personal Protective Equipment (PPE) Usage: Inconsistent use of gowns, eye protection, and masks across multiple departments, particularly in OPD, Pediatrics, Surgical, and Laboratory units.

- Hand Hygiene: Generally good awareness, yet frequent shortages of soap and alcohol-based hand rub at critical care points reduce compliance.

- Environmental Cleaning: Irregular cleaning of high-touch surfaces, equipment, and patient areas; lack of cleaning documentation and supervision.

- Waste Management: Proper segregation practiced; however, sharps containers are often overfilled and hazardous pharmaceutical waste bins are lacking.

- Isolation Facilities: Absence of dedicated isolation corners in several wards limits effective transmission-based precautions.

- Linen and Specimen Handling: Open or uncovered linen containers and lack of spill management protocols increase contamination risks.

Feedback Summary Table for all the case teams based on the IPC monitoring report for the 1st Quarter of 2017 E.C. at Deder General Hospital:

| Case Team | Key IPC Gaps Identified | Recommendations | Responsible Body | Timeline |
| --- | --- | --- | --- | --- |
| OPD, Pediatrics, EOPD | - Incomplete PPE usage (gowns, eye protection)- Missing hand hygiene supplies at care points- Patient transport not controlled | - Conduct PPE refresher training and display reminders- Audit and restock hand hygiene materials- Train and assign focal points for patient transport control | IPC Committee, Unit Heads, Pharmacy Unit | Weeks 1–2 |
| Maternity Ward | - Low consistent use of gowns and eye protection- Occasional lack of soap/hand rub at delivery beds- Unclean equipment and surfaces- Open linen containers- Overfilled sharps containers | - Refresher training on PPE- Ensure hand hygiene supplies at all points- Implement cleaning logs for beds/equipment- Use covered linen containers- Timely sharps disposal | Maternity Lead, Cleaning Supervisor, Environmental Health Team | Within 1 week–Immediate |
| NICU | - Inconsistent use of gowns and eye protection- Hand rub stations empty sometimes- Equipment and incubators not regularly disinfected- Uncovered soiled linens- No isolation corner | - Reinforce full PPE use- Ensure continuous hand rub availability- Implement cleaning logs for equipment- Covered linen bins- Establish isolation corner | NICU Lead, IPC Team, Facility Management | Week 1–Month 1 |
| Surgical Ward | - Inconsistent gowns/eye protection during dressing changes- Missed hand hygiene moments- Unclean bedrails and instruments- Overfilled sharps containers- Open linen containers | - PPE refresher training- Ensure soap/hand rub availability- Daily cleaning checklists- Sharps container monitoring- Provide covered linen bins | Ward Head, IPC Team, Cleaning Supervisor, Environmental Health | Week 1–Immediate |
| Laboratory | - Inconsistent lab coat and eye protection use- Occasional missed hand hygiene after glove removal- Unclean workbenches and equipment- Overfilled sharps containers- No spill management protocol | - PPE and hand hygiene refresher training- Ensure supplies available- Daily cleaning logs- Sharps container replacement- Develop spill SOP and train staff | Lab Supervisor, IPC Team, Environmental Health | Week 1–Within 2 weeks |
| Pharmacy | - Inconsistent gowns and masks use- Handwashing stations lack supplies- Unclean counters and equipment- No hazardous waste bins- Improper medicine storage near sinks/waste | - PPE refresher training- Restock hand hygiene supplies- Cleaning logs for counters- Procure hazardous waste bins- Reorganize medicine storage | Pharmacy Lead, IPC Team, Procurement Office | Week 1–Within 2 weeks |

Recommendations and Actions:

We urge each team to prioritize the following actions immediately:

- Conduct refresher IPC trainings focused on correct and consistent PPE use and hand hygiene.

- Ensure continuous availability and proper placement of hand hygiene supplies.

- Implement and maintain daily environmental cleaning checklists with supervisory sign-off.

- Improve sharps container monitoring and timely disposal to prevent occupational hazards.

- Procure and deploy appropriate chemical and hazardous waste bins.

- Establish low-cost isolation corners where possible within wards.

- Develop and train on spill management protocols especially in Laboratory and patient care areas.

- Assign IPC focal persons in each team to coordinate activities and liaise with the IPC office.

- Engage actively in monthly IPC audits and promptly implement corrective actions.

Conclusion:

Your cooperation and dedication are essential to strengthening IPC compliance and safeguarding the health of our patients, staff, and visitors. We trust that with focused effort and teamwork, we will close the gaps between policy and practice.

Please acknowledge receipt of this feedback and submit your team-specific action plans within two weeks.

Sincerely,
Ibrahim Tahir
Infection Prevention and Control Officer
Deder General Hospital