QI PROJECT PDSA CYCLES REPORT FORM

QI PROJECT LEADER: Nuredin Yigezu (MPH)

END DATE: 20/10/2017EC

START DATE:21/10/ 2016 EC

QIP: Reduce supply chain Inefficiency from a median of 17% to less than 5% from  21/10/2016 to  20/10/2017

.

| CHANGE IDEA: Implement quarterly inventory reviews |  |  | PDSA 1: CYCLE III |  |  |  | DATE: 30/07/2017EC |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PLAN |  |  |  |  |  |  |  |  |
| WHAT IS THE PURPOSE OF THIS CYCLE? (Check one) |  |  | DEVELOP |  | - TEST |  | IMPLEMENT |  |
| WHAT IS THE OBJECTIVE OF THIS CYCLE? WHAT QUESTIONS DO YOU WANT TO ANSWER? WHAT ARE YOUR PREDICTIONS? |  |  |  |  |  |  |  |  |
| Objective: Reduce total supply chain inefficiency from 6% to less than 5% through structured quarterly inventory review and enhanced follow-up on identified gaps. Questions to Answer: The supply chain inefficiency will drop by 1% percentage points (from 6% to <5%) as a result of quarterly inventory review? Predictions: The cycle will lead to a 1% improvement, achieving <5% total inefficiency by the end of the quarter.. |  |  |  |  |  |  |  |  |
| LIST TASKS NECESSARY TO SET UP AND CONDUCT THE TEST (THINK ‘ONENESS’ AND ‘DROP TWO’) |  |  |  |  |  |  |  |  |
| What? (Specifc task) | How? (Checklist, tally sheet) |  |  | Who? (Name or role) |  | When? (Times, dates - be specifc) |  | Where? (Program, location site - be specifc) |
| - Conducting quarterly inventory reviews | EAPTS report |  |  | Rediwan S. (Data Collector) |  | QUARTERLY |  | Pharmacy |
| - Gap Assessment Across 11 supply chain Areas | - Reviewing EAPTS, Bin Cards, Model 19 |  |  | Rediwan S. |  | Quarterly |  | Finance |
| OUTLINE YOUR PDSA DATA COLLECTION PLAN (WHAT, HOW, WHO WHEN AND WHERE) |  |  |  |  |  |  |  |  |
| What data will be collected? | How? (Checklist, tally sheet) |  |  | Who? (Name or role) |  | When? (Times, dates – be specifc) |  | Where will the data be recorded? |
| EAPTS TRANSACTION DATA | Model 19, Bincard, Eapts Transactions, Observation |  |  | Rediwan S. |  | Quarterly |  | Pharmacy and Finance |
|  |  |  |  | DO |  |  |  |  |
| WHAT DID YOU OBSERVE DURING THE TEST? WERE THERE ANY UNEXPECTED OBSERVATIONS OR ISSUES? WHAT WENT WELL? |  |  |  |  |  |  |  |  |
| #### Observations - Notable improvements in Inventory Management, Procurement, Storage, and Demand Forecasting due to regular inventory reviews. - Departments actively engaged in performance tracking using standard tools (Model 19, Bin Cards, EAPTS). #### What Went Well - Overall inefficiency reduced from 6.0% to 5.0%. - Use of digital tools and standardized data collection enhanced accuracy. - Quarterly inventory reviews improved stock accuracy and interdepartmental communication. #### Unexpected Observations/Issues - Persistent inefficiencies in Demand Forecasting, Procurement, and Communication & Coordination. - Absence of formal KPI monitoring, contract reviews, and emergency communication protocols. - Limited clinical team feedback and lack of routine audits. #### Challenges - No defined minimum/maximum stock policies. - Inconsistent quarterly inventory reviews prior to this cycle. - Lack of formal interdepartmental coordination frameworks. - Limited oversight from the Drug and Therapeutics Committee (DTC) on procurement and order verification. |  |  |  |  |  |  |  |  |
| STUDY |  |  |  |  |  |  |  |  |
| ANALYZE YOUR DATA AND DESCRIBE THE RESULTS. HOW DO THE RESULTS COMPARE WITH YOUR PREDICTIONS? WHAT DID YOU LEARN FROM THIS CYCLE? |  |  |  |  |  |  |  |  |
|  Quarterly inventory reviews contributed positively to reducing inefficiencies but slightly missed the <5% target.  Improvements in inventory accuracy and technology utilization are promising but must be further strengthened.  Addressing persistent gaps in forecasting, procurement practices, and communication is critical.  Formal KPI tracking are necessary for sustained gains.  Enhanced clinical feedback and routine audits will support continuous improvement. No.; Area of Inefficiency; Contribution (%); Cost (ETB). 1; Demand Forecasting; 1.4%; 13,490. 2; Procurement Efficiency; 1.1%; 10,606. 3; Communication & Coordination; 1.0%; 9,642. 4; Financial Management & Cost Control; 0.5%; 4,821. 5; Storage Practice Inefficiency; 0.3%; 2,893. 6; Inventory Management; 0.3%; 2,893. 7; Technology & System Integration; 0.2%; 1,929. 8; Wastage Reduction; 0.2%; 1,929. 9; Monitoring & Reporting; 0.15%; 1,446. 10; Dispensing Practice Inefficiency; 0.15%; 1,446. Total; 5.0%; 48,185. |
| ACT |  |  |  |  |  |  |  |  |
| Adapt: Sustain quarterly inventory review as they have shown clear impact on reducing supply chain inefficiency. |  |  |  |  |  |  |  |  |
| ADAPT (note changes for next cycle |  | ADOPT |  |  |  |  | ABANDON |  |

Reported by: Rediwan S.	Case Team: QI team	Date: MEGABIT 30, 2017E.C

PDSA 1 CYCLE III

Conducting supply chain meeting

PDSA 1 CYCLE  I

Conducting supply chain meeting