QI PROJECT PDSA CYCLES REPORT FORM

QI PROJECT LEADER: Nuredin Yigezu (MPH)

END DATE: 20/10/2017EC

START DATE:21/10/ 2016 EC

QIP: Reduce supply chain Inefficiency from a median of 17% to less than 5% from  21/10/2016 to  20/10/2017

.

| CHANGE IDEA: Conducting Quarterly Supply Chain Meetings |  |  | PDSA 1: CYCLE IV |  |  |  | DATE: 30/10/2017EC |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PLAN |  |  |  |  |  |  |  |  |
| WHAT IS THE PURPOSE OF THIS CYCLE? (Check one) |  |  | DEVELOP |  | - TEST |  | IMPLEMENT |  |
| WHAT IS THE OBJECTIVE OF THIS CYCLE? WHAT QUESTIONS DO YOU WANT TO ANSWER? WHAT ARE YOUR PREDICTIONS? |  |  |  |  |  |  |  |  |
| Objective: Reduce total supply chain inefficiency from 5% to less than 5% through structured quarterly supply chain meetings and enhanced follow-up on identified gaps. Questions to Answer: Do implementing supply chain meeting supply chain inefficiency from 5% to <5% ? Predictions: If these interventions are maintained, the supply chain inefficiency rate will fall from 5% to below 5% |  |  |  |  |  |  |  |  |
| LIST TASKS NECESSARY TO SET UP AND CONDUCT THE TEST (THINK ‘ONENESS’ AND ‘DROP TWO’) |  |  |  |  |  |  |  |  |
| What? (Specifc task) | How? (Checklist, tally sheet) |  |  | Who? (Name or role) |  | When? (Times, dates - be specifc) |  | Where? (Program, location site - be specifc) |
| - Conducting Inventory Review | - Reviewing the Quarterly Inventory using the structrured EAPTS checklist |  |  | Rediwan S. (Data Collector) |  | QUARTERLY |  | Pharmacy |
| - Gap Assessment Across 11 supply chain Areas | - Reviewing EAPTS, Bin Cards, Model 19 |  |  | Rediwan S. |  | Quarterly |  | Finance |
| OUTLINE YOUR PDSA DATA COLLECTION PLAN (WHAT, HOW, WHO WHEN AND WHERE) |  |  |  |  |  |  |  |  |
| What data will be collected? | How? (Checklist, tally sheet) |  |  | Who? (Name or role) |  | When? (Times, dates – be specifc) |  | Where will the data be recorded? |
| EAPTS TRANSACTION DATAS | Model 19, Bincard, Eapts Transactions, Observation |  |  | Rediwan S. |  | Quarterly |  | Pharmacy and Finance |
|  |  |  |  | DO |  |  |  |  |
| WHAT DID YOU OBSERVE DURING THE TEST? WERE THERE ANY UNEXPECTED OBSERVATIONS OR ISSUES? WHAT WENT WELL? |  |  |  |  |  |  |  |  |
| What Was Done: - Inventory reviewing is done. - Digital tracking (EAPTS) used in more pharmacy points. - Supplier evaluations were conducted based on delivery accuracy and timeliness. - Audit and reporting templates standardized. What Went Well: - Inefficiency reduced from 5% to 3.12%. - Reduced emergency procurement by 50%. - Better accountability from departments due to KPI sharing. Challenges: - Still some inefficiencies were witnessed in some areas |  |  |  |  |  |  |  |  |
| STUDY |  |  |  |  |  |  |  |  |
| ANALYZE YOUR DATA AND DESCRIBE THE RESULTS. HOW DO THE RESULTS COMPARE WITH YOUR PREDICTIONS? WHAT DID YOU LEARN FROM THIS CYCLE? |  |  |  |  |  |  |  |  |
| Expected Outcome: Inefficiency rate drops below 5% Actual Outcome: Inefficiency rate reduced to 3.12%, with associated cost at 42,000 ETB Key Findings: - Improved monitoring and digital system usage had the highest impact. - Most inefficiency gains came from improved procurement planning and supplier engagement. - Communication delays and outdated SOPs in emergency requests remain a risk area. Lesson Learned: - Continued quarterly meetings and focused KPIs lead to measurable improvements. - Need for full institutionalization of SOPs and system training for sustained gains. No.; Area of Inefficiency; Contribution to Inefficiency (%); Estimated Cost (ETB). 1; Procurement Efficiency; 0.85%; 11,340. 2; Inventory Management; 0.40%; 5,350. 3; Demand Forecasting; 0.50%; 6,675. 4; Supplier and Distribution; 0.30%; 4,005. 5; Financial Management & Cost Efficiency; 0.25%; 3,150. 6; Monitoring and Reporting; 0.10%; 1,260. 7; Technology and System Integration; 0.12%; 1,512. 8; Communication and Coordination; 0.20%; 2,520. 9; Wastage Reduction; 0.15%; 1,890. 10; Storage Practice Inefficiency; 0.05%; 630. 11; Dispensing Practice Inefficiency; 0.10%; 1,260. Total; 3.12%; 41,592. |
| ACT |  |  |  |  |  |  |  |  |
| Adapt: Sustain quarterly supply chain meetings as they have shown clear impact on reducing supply chain inefficiency. |  |  |  |  |  |  |  |  |
| ADAPT (note changes for next cycle |  | ADOPT |  |  |  |  | ABANDON |  |

Reported by: Rediwan S.	Case Team: QI team	Date: SENE 30, 2017E.C

PDSA 1 CYCLE IV

Conducting supply chain meeting

PDSA 1 CYCLE III

Conducting supply chain meeting

PDSA 1 CYCLE  I

Conducting supply chain meeting