DEDER GENERAL HOSPITAL

SUPPLY CHAIN INEFFICIENCY ASSESSMENT REPORT

QUARTER 2, 2016 E.C.

BY: DTC COMMITTEE

TAHSAS, 2017EC
DADER, ETHIOPIA

### Table of Contents

Table of Contents

Table of Contents	1

1. Executive Summary	2

2. Introduction	2

3. Objectives of the Assessment	2

4. Methodology	2

5. Cost Calculation Formulas	3

6. PREVIOUS ACTION PLAN IMPLEMENTATION	6

6. Inefficiency Summary Table (Q1 2016EC)	7

7. Risk Assessment	8

8. Discussion	8

9. Action Plan (Q2 2016EC)	8

10. Recommendations	9

11. Conclusion	9

12. References	10

### 1. Executive Summary

This report presents the Quarter 2, 2016EC supply chain inefficiency assessment for Deder General Hospital. Despite improvements in waste reduction and inventory audit practices, key areas such as monitoring, communication, and digital system utilization remain underperforming. The total inefficiency rate has increased to 21%, a 1% rise from the previous quarter. The report also evaluates implementation progress of previous action plans and proposes practical, targeted interventions for improvement.

### 2. Introduction

A well-functioning supply chain ensures availability of essential medicines, cost efficiency, and responsiveness. This quarterly assessment builds on past evaluations and focuses on diagnosing inefficiencies and improving continuity of critical supplies.

### 3. Objectives of the Assessment

The assessment aimed to:

- Conduct a structured analysis of current supply chain performance indicators.

- Identify specific operational gaps causing inefficiencies across the supply chain.

- Evaluate financial impacts and risks associated with these inefficiencies.

- Recommend strategic, evidence-based interventions that are practical and resource-conscious.

- Provide a baseline for continuous quality improvement in inventory, procurement, and logistics functions.

### 4. Methodology

### a) Data Collection Methods

- Document Review: Examined monthly consumption reports, Quarterly Inventory, procurement records, supplier delivery logs, and Bin Card and  stock cards to assess historical performance.

- Direct Observation: Inspected pharmacy storage rooms, inventory shelves, and distribution workflows on-site.

- Key Informant Interviews: Conducted interviews with pharmacy heads, procurement officers, and department heads.

- Checklist-based Assessment: Utilized a customized supply chain performance checklist for standardized evaluation.

### b) Assessment Scope

- Covered Quarter 3, 2015EC (3-month period).

- Included all stages of the supply chain: planning, procurement, storage, inventory management, distribution, and monitoring.

### c) Analysis Techniques

- Numerical scoring and ranking of inefficiency areas based on cost and operational impact.

- Root cause analysis internally.

- Application of cost formulas to quantify inefficiencies and adjust weight percentages.

## 5. Cost Calculation Formulas

Stockouts Cost
Stockouts Cost = Number of Stockouts × Average Cost per Stockout

- Number of Stockouts: Total instances where essential supplies were unavailable.

- Average Cost per Stockout: Estimated cost from lost revenue, emergency procurement, or alternate arrangements.

Excess Inventory Cost
Excess Inventory Cost = Excess Inventory Level × Carrying Cost per Unit

- Excess Inventory Level: Inventory above optimal or required levels.

- Carrying Cost per Unit: Cost of storage, depreciation, insurance, and wastage per unit

- Supplier Communication Cost
Supplier Communication Cost = Number of Communication Errors × Cost per Error

- Number of Communication Errors: Miscommunications with suppliers.

- Cost per Error: Financial impact of delays, re-orders, or incorrect shipments.

Performance Monitoring Cost
Performance Monitoring Cost = Number of Performance Assessments × Cost per Assessment

- Number of Performance Assessments: Reviews or audits conducted.

- Cost per Assessment: Resources (time, labor, documentation) used per review.

Transportation Cost
Transportation Cost = Number of Shipments × Average Cost per Shipment

- Number of Shipments: All supply deliveries made.

- Average Cost per Shipment: Includes vehicle cost, fuel, labor, and logistics.

Poor Inventory Tracking Cost
Poor Inventory Tracking Cost = Number of Inventory Discrepancies × Cost per Discrepancy

- Number of Inventory Discrepancies: Mismatches between records and physical stock.

- Cost per Discrepancy: Includes correction cost, reordering, and delays.

Total Supply Chain Costs
Total Supply Chain Costs = Stockouts Cost + Excess Inventory Cost + Supplier Communication Cost + Performance Monitoring Cost + Transportation Cost + Poor Inventory Tracking Cost

Procurement Inefficiency (%)
= ((Actual Procurement Cost - Benchmark Cost) / Benchmark Cost) × 100

- Compares actual cost to standard/optimal cost.

Inventory Management Inefficiency (%)
= ((Stockouts + Overstocks) / Total Inventory Transactions) × 100

- Measures how often supply is either unavailable or overstocked.

Storage Inefficiency (%)
= (Damaged or Expired Stock / Total Stock) × 100

- Captures the percentage of unusable items due to poor storage.

Demand Forecasting Inefficiency (%)
= (|Actual Demand - Forecast| / Actual Demand) × 100

- Tracks accuracy in predicting demand.

Supplier Inefficiency (%)
= (Late or Incorrect Deliveries / Total Deliveries) × 100

- Measures supplier delivery failures.

Distribution Inefficiency (%)
= (Delayed or Incomplete Deliveries / Total Shipments) × 100

- Shows failures in internal distribution of supplies.

Cost Inefficiency (%)
= ((Actual Supply Chain Costs - Budgeted Costs) / Budgeted Costs) × 100

- Measures overspending against what was planned.

Reporting Inefficiency (%)
= (Delayed Reports / Total Reports) × 100

- Identifies how often reporting is delayed.

Technology and System Integration Inefficiency (%)
= (Manual Processes / Total Processes) × 100

- Reflects use of outdated or non-digital systems.

Communication and Coordination Inefficiency (%)
= [1 - (Communication Failures / Total Communications)] × 100

- Measures breakdown in communication across departments.

Waste Management Inefficiency (%)
= (Unusable or Expired Stock / Total Stock Handled) × 100

- Identifies how much of the total handled stock is wasted.

Dispensing Practice Inefficiency (%)
= (Incorrect or Delayed Dispensing Cases / Total Dispensing Transactions) × 100

- Evaluates issues in giving out supplies or medicines to wards or patients.

# 6. PREVIOUS ACTION PLAN IMPLEMENTATION

| Category | Identified Gap | Strategic Intervention | Responsible Unit | Timeline | Implementation Status |
| --- | --- | --- | --- | --- | --- |
| Inventory Management | EAPTS under-utilized | Conduct monthly EAPTS report reviews and follow-up actions | Pharmacy Unit | Monthly | ✅ Partially Implemented: EAPTS reports were reviewed in 2 of the 3 months. Interpretation and follow-up still inconsistent. |
| Inventory Accuracy | Inconsistent physical counts | Conduct quarterly stock audits and reconcile discrepancies | Pharmacy Unit & DTC | Quarterly | ✅ Implemented: Physical counts conducted; discrepancies noted and partially resolved. |
| Procurement | Lack of regular procurement reviews | Hold structured monthly procurement review meetings | DTC & Procurement Unit | Monthly | ❌ Not Implemented: No documentation of any formal procurement review meetings. |
| Supplier Engagement | No routine supplier performance evaluation | Organize biannual supplier roundtables | Procurement Office | Twice per year | ❌ Not Implemented: No roundtable or supplier evaluation activity conducted. |
| Staff Capacity | Low knowledge of SOPs and stock management | Conduct quarterly on-site staff SOP training workshops | SMT & DTC | Quarterly | ✅ Partially Implemented: One workshop held for pharmacy staff; other departments not yet trained. |
| Emergency Response | No urgent communication protocol utilization | Establish simple emergency supply request communication SOP | DTC | Within 1 month | ❌ Not Implemented: SOP drafted but not yet finalized or disseminated. |
| Forecasting | Prioritization not reviewed quarterly | Introduce quarterly prioritization review based on consumption trends | DTC & Pharmacy Unit | Quarterly | ✅ Implemented: Quantification and prioritization conducted; evidence available. |
| Performance Monitoring | KPIs not tracked regularly | Initiate simple monthly KPI dashboard (stockout, expiry, delay) | DTC | Monthly | ❌ Not Implemented: KPI dashboard not yet initiated or shared with departments. |

### 6. Inefficiency Summary Table (Q1 2016EC)

| Indicator | Score (%) | Gaps Identified | Cost (ETB) | Contribution (%) |
| --- | --- | --- | --- | --- |
| Procurement Efficiency | 80 | Lack of policy review, process delays | 5,000 | 1.5 |
| Inventory Management | 80 | Inadequate audits, under/overstocking | 50,000 | 1.4 |
| Demand Forecasting | 100 | Prioritization not quarterly reviewed | 6,000 | 2.0 |
| Supplier & Distribution Performance | 100 | Discrepancies, limited performance tracking | 10,000 | 1.0 |
| Financial Management & Cost Efficiency | 60 | Lack of cost-saving review mechanisms | 8,000 | 1.2 |
| Monitoring & Reporting | 0 | No KPI review or documentation | 10,000 | 1.3 |
| Technology & System Integration | 0 | EAPTS not actively used, poor digital literacy | 23,000 | 1.4 |
| Communication & Coordination | 0 | Poor link between clinical and store units | 10,000 | 1.5 |
| Waste Reduction | 85 | Limited recycling or separation | 3,000 | 1.3 |
| Storage Practice | 90 | Poor layout, no stock rotation | 1,000 | 1.6 |
| Dispensing Practice | 90 | Poor documentation, no barcode/label check | 2,000 | 1.7 |
| Total | — |  | 128,000 | 21.0 |

Figure 1 ; Supply chain inefficiency rate  quarter 2, 2016 EC

### 7. Risk Assessment

- Operational Delays: Resulting from poor communication and long procurement lead times

- Inventory Shortages: Due to missed prioritization

- Non-compliance Risks: Absence of updated SOPs and policy reviews

- Financial Wastage: Inefficiencies in procurement and poor monitoring lead to uncontrolled cost

### 8. Discussion

EAPTS is functional but under-utilized for analytics and reporting. Monitoring and communication remain critical gaps, with 0% performance in KPI tracking and inter-department collaboration. Procurement efficiency has slightly improved due to early partial review activities, but inconsistencies persist.

Supplier engagement is still ad hoc. Waste and dispensing practices improved, likely due to prior quarter audits and SOP refresher sessions. However, without ongoing review and digital tracking, gains may not be sustainable.

### 9. Action Plan (Q2 2016EC)

| Identified Gap | Root Cause | Strategic Intervention | Responsible Unit | Timeline |
| --- | --- | --- | --- | --- |
| EAPTS under-utilized | Lack of training & supervision | Monthly EAPTS reviews & accountability loop | Pharmacy Unit | Monthly |
| Physical count inconsistencies | No routine audit culture | Quarterly audits with pharmacy–store joint team | Pharmacy & DTC | Quarterly |
| No procurement review | Weak oversight | Structured monthly procurement review meetings | DTC & Procurement | Monthly |
| No supplier evaluation | No scheduled review | Hold biannual supplier roundtable discussions | Procurement Office | Biannual |
| Staff unaware of SOPs | No refresher trainings | Quarterly on-site SOP and logistics refresher trainings | SMT & DTC | Quarterly |
| No emergency protocol used | Lack of clarity on roles | Finalize and disseminate emergency SOP | DTC | 1 Month |
| No quarterly prioritization | No process in place | Review consumption and adjust orders quarterly | DTC & Pharmacy | Quarterly |
| KPIs not tracked | No dashboard | Launch simple KPI dashboard on Excel | DTC | Monthly |

### 10. Recommendations

- Strengthen KPI Monitoring: Introduce routine dashboard with trend analysis

- Institutionalize Supplier Review: Formalize review schedule linked to contract renewal

- Boost EAPTS Use: Reinforce accountability, ensure regular report interpretation

- Enhance Communication: Schedule joint logistics-clinical reviews monthly

- Prioritization Every Quarter: Make it part of DTC quarterly meeting agenda

- Digital SOP Repository: Share updated SOPs via hospital LAN or WhatsApp

### 11. Conclusion

Quarter 2, 2016EC saw marginal progress in supply chain efficiency. While the overall performance is still within the moderate range (efficiency score: 64%), the 1% rise in inefficiency to 21% warrants attention. With structured interventions in digital utilization, performance tracking, and team-based review, the hospital can expect significant efficiency gains in future quarters.

### 12. References

- WHO. (2017). Health System Strengthening: Supply Chain Toolkit. Geneva.

- USAID | DELIVER PROJECT. (2011). Logistics Indicators Assessment Tool (LIAT).

- UNICEF Supply Division. (2019). Inventory Management Best Practices.

- Ethiopia EPSA. (2022). EAPTS User Manual.

- MSH. (2012). Quantifying the Cost of Inefficiency in Public Health Supply Chains.

- Global Fund. (2021). Procurement and Supply Chain Management Toolkit.

- Gavi. (2020). Digital Transformation of Vaccine Supply Chains.

- Ethiopia FMOH. (2021). Health Commodity Management Manual.

- GS1. (2020). Standards in Healthcare Supply Chains.

- APICS. (2020). APICS Dictionary, 16th Edition.

- Management Sciences for Health. (2017). Supply Chain Performance Assessment.

- World Bank. (2020). Public Procurement Assessment Report: Ethiopia.

- PATH. (2018). Digital Health Supply Chain Interventions.

- OECD. (2016). Public Procurement Review of Ethiopia.

- WHO. (2015). Medicines Supply Chain and Logistics Management Guidelines.

- USAID. (2020). Visibility and Analytics Network (VAN) Overview.

- JSI Research & Training Institute. (2019). Improving Commodity Availability.

- SAPICS. (2019). Public Health Supply Chain Conference Proceedings.

- Ethiopian Pharmaceutical Association. (2021). Pharmacy Practice Guidelines.

- McKinsey & Company. (2020). Transforming Public Procurement with Digital Tools.