# DEDER GENERAL HOSPITAL

## SUPPLY CHAIN INEFFICIENCY ASSESSMENT REPORT

### QUARTER 3, 2015EC

By: DTC Committee

Deder,  Ethiopia

## Table of Contents

Contents

Table of Contents	1

1. Executive Summary	2

2. Introduction	2

3. Objectives of the Assessment	2

4. Methodology	3

5. Cost Calculation Formulas	3

6. Inefficiency Summary Table (Q3 2015EC)	6

7. Assessment Results	7

8. Risk Assessment	8

9. Discussion	8

10. Action Plan	10

11. Recommendations and Utilization Plan	10

12. Conclusion	11

13. References	12

## 1. Executive Summary

This comprehensive report presents a detailed evaluation of the current supply chain management system of Deder General Hospital, conducted during Quarter 3 of 2015EC. The primary goal was to assess operational performance, identify inefficiencies, and determine associated cost implications. Inefficiencies in procurement, inventory tracking, communication, and performance monitoring were identified as critical challenges, leading to stockouts, overstocking, increased operational costs, and delayed services. By applying structured metrics, cost formulas, and international supply chain benchmarks, this report outlines a corrective roadmap aimed at improving system-wide efficiency. With focused interventions and strengthened accountability, contributing to improved patient care, timely service delivery, and responsible resource management.

## 2. Introduction

Efficient supply chain management is vital for the continuous provision of quality healthcare services. At Deder General Hospital, supply chain inefficiencies have resulted in stockouts, excess inventory, and increased procurement costs, adversely affecting patient care and operational efficiency. This assessment seeks to identify these inefficiencies and provide a structured approach to reduce supply-related costs by 20% within a one-year timeframe.

## 3. Objectives of the Assessment

The assessment aimed to:

- Conduct a structured analysis of current supply chain performance indicators.

- Identify specific operational gaps causing inefficiencies across the supply chain.

- Evaluate financial impacts and risks associated with these inefficiencies.

- Recommend strategic, evidence-based interventions that are practical and resource-conscious.

- Provide a baseline for continuous quality improvement in inventory, procurement, and logistics functions.

## 4. Methodology

### a) Data Collection Methods

- Document Review: Examined monthly consumption reports, Quarterly Inventory, procurement records, supplier delivery logs, and Bin Card and  stock cards to assess historical performance.

- Direct Observation: Inspected pharmacy storage rooms, inventory shelves, and distribution workflows on-site.

- Key Informant Interviews: Conducted interviews with pharmacy heads, procurement officers, and department heads.

- Checklist-based Assessment: Utilized a customized supply chain performance checklist for standardized evaluation.

### b) Assessment Scope

- Covered Quarter 3, 2015EC (3-month period).

- Included all stages of the supply chain: planning, procurement, storage, inventory management, distribution, and monitoring.

### c) Analysis Techniques

- Numerical scoring and ranking of inefficiency areas based on cost and operational impact.

- Root cause analysis internally.

- Application of cost formulas to quantify inefficiencies and adjust weight percentages.

### d) Validation

- Findings validated through team review meetings.

- Inputs from clinical and non-clinical units ensured accuracy across functions.

This mixed-method approach provided a comprehensive understanding of supply chain challenges and informed practical, context-appropriate solutions.

## 5. Cost Calculation Formulas

Stockouts Cost
Stockouts Cost = Number of Stockouts × Average Cost per Stockout

- Number of Stockouts: Total instances where essential supplies were unavailable.

- Average Cost per Stockout: Estimated cost from lost revenue, emergency procurement, or alternate arrangements.

Excess Inventory Cost
Excess Inventory Cost = Excess Inventory Level × Carrying Cost per Unit

- Excess Inventory Level: Inventory above optimal or required levels.

- Carrying Cost per Unit: Cost of storage, depreciation, insurance, and wastage per unit

- Supplier Communication Cost
Supplier Communication Cost = Number of Communication Errors × Cost per Error

- Number of Communication Errors: Miscommunications with suppliers.

- Cost per Error: Financial impact of delays, re-orders, or incorrect shipments.

Performance Monitoring Cost
Performance Monitoring Cost = Number of Performance Assessments × Cost per Assessment

- Number of Performance Assessments: Reviews or audits conducted.

- Cost per Assessment: Resources (time, labor, documentation) used per review.

Transportation Cost
Transportation Cost = Number of Shipments × Average Cost per Shipment

- Number of Shipments: All supply deliveries made.

- Average Cost per Shipment: Includes vehicle cost, fuel, labor, and logistics.

Poor Inventory Tracking Cost
Poor Inventory Tracking Cost = Number of Inventory Discrepancies × Cost per Discrepancy

- Number of Inventory Discrepancies: Mismatches between records and physical stock.

- Cost per Discrepancy: Includes correction cost, reordering, and delays.

Total Supply Chain Costs
Total Supply Chain Costs = Stockouts Cost + Excess Inventory Cost + Supplier Communication Cost + Performance Monitoring Cost + Transportation Cost + Poor Inventory Tracking Cost

Procurement Inefficiency (%)
= ((Actual Procurement Cost - Benchmark Cost) / Benchmark Cost) × 100

- Compares actual cost to standard/optimal cost.

Inventory Management Inefficiency (%)
= ((Stockouts + Overstocks) / Total Inventory Transactions) × 100

- Measures how often supply is either unavailable or overstocked.

Storage Inefficiency (%)
= (Damaged or Expired Stock / Total Stock) × 100

- Captures the percentage of unusable items due to poor storage.

Demand Forecasting Inefficiency (%)
= (|Actual Demand - Forecast| / Actual Demand) × 100

- Tracks accuracy in predicting demand.

Supplier Inefficiency (%)
= (Late or Incorrect Deliveries / Total Deliveries) × 100

- Measures supplier delivery failures.

Distribution Inefficiency (%)
= (Delayed or Incomplete Deliveries / Total Shipments) × 100

- Shows failures in internal distribution of supplies.

Cost Inefficiency (%)
= ((Actual Supply Chain Costs - Budgeted Costs) / Budgeted Costs) × 100

- Measures overspending against what was planned.

Reporting Inefficiency (%)
= (Delayed Reports / Total Reports) × 100

- Identifies how often reporting is delayed.

Technology and System Integration Inefficiency (%)
= (Manual Processes / Total Processes) × 100

- Reflects use of outdated or non-digital systems.

Communication and Coordination Inefficiency (%)
= [1 - (Communication Failures / Total Communications)] × 100

- Measures breakdown in communication across departments.

Waste Management Inefficiency (%)
= (Unusable or Expired Stock / Total Stock Handled) × 100

- Identifies how much of the total handled stock is wasted.

Dispensing Practice Inefficiency (%)
= (Incorrect or Delayed Dispensing Cases / Total Dispensing Transactions) × 100

- Evaluates issues in giving out supplies or medicines to wards or patients.

## 6. Inefficiency Summary Table (Q3 2015EC)

| No. | Assessment Area | Cost (ETB) | % Contribution |
| --- | --- | --- | --- |
| 1 | Procurement Efficiency inefficiency | 9,000 | 1.50% |
| 2 | Inventory Management inefficiency | 7,440 | 1.24% |
| 3 | Demand Forecasting inefficiency | 6,660 | 1.11% |
| 4 | Supplier and Distribution Performance inefficiency | 7,800 | 1.30% |
| 5 | Financial Management and Cost inefficiency | 8,160 | 1.36% |
| 6 | Monitoring and Reporting inefficiency | 9,000 | 1.50% |
| 7 | Technology and System Integration inefficiency | 4,680 | 0.78% |
| 8 | Communication and Coordination inefficiency | 5,460 | 0.91% |
| 9 | Wastage Reduction inefficiency | 3,540 | 0.59% |
| 10 | Storage Practice Inefficiency | 5,460 | 0.91% |
| 11 | Dispensing Practice Inefficiency | 4,800 | 0.80% |
| Total |  | 60,000 | 12.00% |

Figure 1: Supply chain inefficiency rate  Quarter 3,2015 EC

## 7. Assessment Results

Key inefficiency areas identified include:

- Procurement: Absence of structured timelines, lack of supplier contracts, and cost overruns.

- Inventory Management: Inadequate demand forecasting, no standardized stock levels, and reliance on manual tracking.

- Supplier and Distribution: Limited communication and absence of performance monitoring for suppliers.

- Technology Use: Under-utilization of digital inventory tools and lack of automated alerts.

- Monitoring and Reporting: Infrequent performance reviews and inconsistent data reporting.

- Coordination and Communication: Poor interdepartmental communication resulting in delayed urgent responses.

- Storage and Dispensing: Irregular audits, high discrepancy rates, and weak stock rotation practices.

## 8. Risk Assessment

The existing inefficiencies pose significant risks:

- Inventory Shortages: Leading to delayed or denied patient care.

- Excess Inventory: Causing wastage from expired stock and higher carrying costs.

- Supplier Dependency: Over-reliance on single suppliers without contingency plans.

- Operational Delays: Inefficient workflows and lack of real-time data slowing decisions.

- Financial Waste: Emergency orders, duplicate purchases, and poor budgeting increase costs.

- Data Inaccuracy: Manual entries without reconciliation produce unreliable stock data.

# 9. Discussion

The supply chain inefficiency assessment conducted for Quarter 3, 2015EC at Deder General Hospital has revealed multiple operational and systemic gaps across key areas. While inefficiencies varied in intensity, certain categories—such as procurement, inventory management, demand forecasting, and coordination—demonstrated recurring patterns that significantly contributed to service interruptions, delayed responses, and wastage of resources.

A key observation from this quarter’s findings was the persistent gap in inventory management, where records were poorly maintained and stock audits were inconsistently conducted. This resulted in both overstocking and stockouts, which directly impacted service delivery and increased holding costs. Poor inventory tracking also led to discrepancies between reported and actual stock levels, revealing the need for better oversight and digitized tools like EAPTS.

Although forecasting and quantification are officially conducted only once a year—typically in Quarter 1 of the new budget cycle, their impact extends across all quarters, especially when implementation is not adjusted based on real-time needs and program priorities. The data from this quarter showed that while annual quantification may have been completed earlier in the year, prioritization of supply items during actual execution was not responsive to current consumption trends or emerging gaps. This disconnection between forecasted need and real-time prioritization resulted in frequent stockouts of high-demand items and accumulation of less-needed items.

The procurement process also showed serious inefficiencies. Lack of structured supplier contracts and delays in approvals were common, leading to irregular procurement cycles. Emergency procurement continued to consume a large share of budget and time, pointing to the absence of preventive strategies such as framework agreements or buffer stock policies.

Similarly, supplier and distribution performance remained weak, with late deliveries and inconsistent order fulfillment. In the absence of a performance monitoring mechanism for suppliers, there were no consequences or feedback mechanisms in place, further eroding reliability.

Another key inefficiency was the underutilization of digital systems such as EAPTS. Though the system was available, it was not consistently used for transaction recording, analysis, or generating real-time alerts. Manual processes led to delays in decision-making and compromised the accuracy of records.

Coordination and communication gaps also hindered the efficiency of supply operations. Departments were often not consulted in decisions around item reallocation or urgent requests, which undermined responsiveness and team accountability. Poorly defined roles and lack of regular communication platforms further weakened interdepartmental collaboration.

The monitoring and reporting systems were underdeveloped, with no consistent follow-up on indicators such as order fill rates, expiry rates, or turnaround time for requisitions. Without reliable data, the hospital was unable to identify trends early or correct systemic failures in a timely manner.

On a broader level, the total supply chain inefficiency was estimated at 12% of the quarterly supply cost, signifying substantial resource loss. However, the findings also provide a critical baseline for change. Gaps such as stock imbalances, irregular reporting, and limited supplier engagement are all actionable areas that can be improved with minimal additional resources, given the right leadership attention and strategic planning.

In conclusion, while forecasting is structured annually, its effectiveness depends on how well prioritization, follow-up, and implementation decisions are made throughout the year. Quarter 3 demonstrated that without dynamic review and adjustment mechanisms, even accurate forecasts can fail to meet program needs. Strengthening communication, institutionalizing quarterly reviews, and maximizing use of digital tools will be essential to shift from reactive to proactive supply chain management in the hospital.

## 10. Action Plan

| Identified Gap | Strategic Intervention | TIME OF IMPLEMENTATION | RESPONSIBLE BODY |
| --- | --- | --- | --- |
| Inventory outcome and EAPTS transaction not reviewed | EAPTS report review | QUARTER 4, 2015 | DTC |
| No periodic cost and procurement cycle evaluation | Monthly procurement process review | QUARTER 4, 2015 | DTC |
| No formal inventory check or reconciliation process | Quarterly stock audits | QUARTER 4, 2015 | DTC |
| Poor supplier engagement and lack of structured feedback | Supplier roundtables | QUARTER 4, 2015 | DTC |
| Low awareness of standard procedures among staff | Staff training workshops | QUARTER 4, 2015 | DTC |
| Lack of defined process for urgent supply requests | Emergency communication SOP | QUARTER 4,2015 | DTC |

## 11. Recommendations and Utilization Plan

- Implement a Digital Inventory System: For real-time stock tracking and automated alerts to minimize stockouts and overstocking.

- Automate Reporting: Deploy automated performance reports to facilitate timely decision-making.

- Establish KPIs: Regularly monitor critical indicators such as stockout rates, procurement lead times, and cost variances.

- Enhance Supplier Engagement: Hold periodic supplier meetings to improve communication and performance.

- Train Staff: Conduct continuous training on supply chain best practices and technology use.

- Strengthen Audits: Institutionalize quarterly stock audits and reconciliation procedures.

- Improve Urgent Requests: Define clear communication protocols for emergency procurement and stock replenishment.

## 12. Conclusion

This assessment reveals critical inefficiencies in Deder General Hospital’s supply chain management that directly affect patient care and operational cost. By adopting the recommended strategic interventions, particularly through digitalization, strengthened communication, and rigorous monitoring, the hospital can significantly reduce inefficiencies . A strong, accountable supply chain framework will ensure continuity of essential medical supplies, promote cost-effectiveness, and improve overall healthcare quality.

## 13. References

- Chopra, S., & Meindl, P. (2019). Supply Chain Management: Strategy, Planning, and Operation. Pearson.

- Simchi-Levi, D., Kaminsky, P., & Simchi-Levi, E. (2007). Designing and Managing the Supply Chain. McGraw-Hill.

- WHO. (2011). Model Guidelines for Medicine Supply Management. World Health Organization.

- USAID DELIVER PROJECT. (2014). Logistics Management Information Systems (LMIS) Toolkit.

- APICS. (2020). APICS Dictionary, 16th Edition.

- Heizer, J., Render, B., & Munson, C. (2017). Operations Management: Sustainability and Supply Chain Management. Pearson.

- Harland, C. M. (1996). Supply Chain Management: Relationships, Chains and Networks. British Journal of Management.

- Global Fund. (2015). Procurement and Supply Chain Management Guide.

- Krafcik, J. F. (1988). Triumph of the Lean Production System. Sloan Management Review.

- Council of Supply Chain Management Professionals (CSCMP). (2018). Supply Chain Management Terms and Glossary.