Dader, Eastern Ethiopia

June 2016E.C

i

DEDER GENERAL HOSPITAL

HEALTH SERVICE QUALITY IMPROVEMENT PROJECT

PROJECT TITLE: REDUCE SUPPLY CHAIN INEFFICIENCY

REGION: OROMIA
HEALTH FACILITY: DEDER GENERAL HOSPITAL
DATE: ___________________

### LIST OF QUALITY IMPROVEMENT TEAM MEMBERS

| S/N | Name | Responsibility | Remarks |
| --- | --- | --- | --- |
| 1. | Nureddin Yigezu (BSc, MPH) | CEO & team leader |  |
| 2. | Dr. Derese Gosa (MD) | Medical Director |  |
| 3. | Obsa Usmail | Data collector |  |
|  | Redwan Sharafuddin | Secretory |  |
| 4. | Hamza Jemal | Member |  |
| 5. | Abdi Tofik | Member |  |
| 6. | Ahmadnur Jibril | Member |  |
| 7. | Dr Dawit Seifu | Member |  |
| 8. | Abdalla Aliyi | Member |  |
| 9. | Alamuudin Usmaa'el | Member |  |
| 10. | Nuree Jamaal | Member |  |
| 11. | Mohaammad Shamsheediin | Member |  |
| 12. | Dine Baker |  |  |

### INTRODUCTION

Effective supply chain management is crucial in healthcare facilities to ensure the availability of essential medical supplies while managing costs effectively. At Deder General Hospital, inefficiencies in the supply chain have led to stockouts, excess inventory, and increased procurement costs, adversely affecting patient care. This project aims to enhance the supply chain processes by streamlining procurement, improving inventory management, and fostering supplier relationships. The goal is to reduce supply chain-related costs by 20% over the next year, ensuring the timely availability of quality supplies for optimal patient care.

Organization’s   Mission, Vision, Scope of Service

- Ergama (Mission)

To reduce morbidity, mortality and disability then improve the health status of people in the catchment area through providing comprehensive rehabilitative, promotive and curative health services via integrated collaborative with all stack holder.

- Mul’ata ( Vision):

See healthy productive and prosperous people

Problem identification and prioritization Matrix

| SN | Lists of problems identified | Prioritization criteria |  |  |  | Rank |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | magnitude | Feasibility | Importance | Total |  |
|  | Stockouts of essential supplies | 5 | 5 | 4 | 14 | 1 |
| 1 | Excess inventory | 3 | 3 | 5 | 11 | 4 |
| 2 | Inefficient supplier communication | 3 | 4 | 4 | 11 | 4 |
| 3 | Lack of performance monitoring | 4 | 4 | 4 | 12 | 3 |
| 4 | High transportation costs | 2 | 3 | 3 | 8 | 5 |
| 5 | Poor inventory tracking | 5 | 5 | 3 | 13 | 2 |

PROBLEM STATEMENT

Inefficiencies in the supply chain at Deder General Hospital have resulted in frequent stockouts of essential medical supplies, excess inventory, and high transportation costs. These issues compromise patient care and increase operational expenses. To enhance the hospital's operational efficiency and improve patient outcomes, it is crucial to address these inefficiencies by streamlining the supply chain processes.

AIM STATEMENT

The Deder General Hospital QI Team aims to reduce supply chain inefficiency from the current median of 17% to <5% from June 21, 2016, to June 20, 2018.

Fishbone Diagram

Inventory Management

Supplier/Vendor Issues

Processes/LogisticsIssues

Inefficient delivery routes

Lack of demand forecasting

Unreliable vendors

Inaccurate stock levels

Lack of competitive bidding

Ineffective inventory control policies

No negotiated volume discounts

Long lead times for deliveries

Storage facility constraints

Inaccurate stock levels

Manual tracking errors

Inadequate accountability

Lack of electronic tracking for supplies

Environmental damage to supplies

Insufficient staff training

Outdated inventory management systems

Fluctuations in demand

Environmental Factors

staff

Equipment/Technology

Figure 1: To reduce supply chain inefficiency from the current median of 17% to <5% from June 21, 2016, to June 20, 2018.

Unscheduled or inconsistent supply deliveries

Lack of standard operating procedures

Poor communication

1 Driver

0

2 Driver

0

Change ideas

AIM

inventory tracking

Demand Forecasting and Inventory Management

Inventory Management

Inventory reordering processes

Procurement and Vendor Relationships

Conduct regular meeting

Supplier/Vendor Issues

to Reduce procurement costs by 15% from June 21, 2016 to June 20, 2018 .

Conduct regular meeting

Processes/Logistics Issues

Logistics and Distribution Efficiency

Efficient delivery scheduling

Optimized transportation routes

Monitoring for expired or damaged stock

Waste and Loss Reduction

staff

Clear policies on stock handling and rotation

Employee training

Figure 2: To reduce supply chain inefficiency from the current median of 17% to <5% from June 21, 2016, to June 20, 2018.

Based on the prioritization matrix, the following five change ideas will be implemented:

- Conduct regular supply chain meetings

- Establish a reliable inventory management system

- Foster strong supplier relationships

- Implement performance monitoring mechanisms

- Train staff on effective supply chain practices

MEASURES

Outcome Measurement

- Percentage Reduction in Supply Chain Costs

Process Measures

- Number of regular supply chain meetings conducted

- Number of suppliers actively engaged

- Reduction in stockouts

- Improvement in inventory turnover rates

MEASURES/INDICATORS

| Aim | Outcome Measure | Change Ideas | Process Measures | Balancing Measures |
| --- | --- | --- | --- | --- |
| To reduce supply chain inefficiency from the current median of 17% to <5% from June 21, 2016, to June 20, 2018. | Percentage Reduction in Supply Chain Costs | Conduct regular supply chain meetings | Number of meetings conducted | Total number of scheduled meetings |
|  | % of stockouts reduced | Establish a reliable inventory management system | Reduction in stockouts | Total number of stockouts in previous periods |
|  | Inventory turnover rate improvement | Foster strong supplier relationships | Number of suppliers actively engaged | Supplier response times |

IMPLEMENTATION PLAN

| S/N | Change Ideas/Interventions | Process Measure | Where | Who (Responsible Body) | When | How |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Conduct regular supply chain meetings |  | Deder GH | Supply Chain Manager & QI Team | June 21, 2016 | Schedule and conduct monthly supply chain meetings |
| 2 | Establish a reliable inventory management system |  | Deder GH | Inventory Manager | June 21, 2016 | Implement inventory management software and train staff |
| 3 | Foster strong supplier relationships |  | Deder GH | Procurement Officer | June 21, 2016 | Develop agreements and communication channels with key suppliers |
| 4 | Implement performance monitoring mechanisms |  | Deder GH | Quality Improvement Team | June 21, 2016 | Establish KPIs for supply chain performance and monitor them |
| 5 | Train staff on effective supply chain practices |  | Deder GH | Training Coordinator | June 21, 2016 | Conduct workshops on supply chain management for relevant staff |

OUTCOME MEASUREMENT DATA COLLECTION PLAN

| AIM | Data Source (Where) | Data Collection Method (How) | Time (When) | Responsible for DC |
| --- | --- | --- | --- | --- |
| To reduce supply chain inefficiency from the current median of 17% to <5% from June 21, 2016, to June 20, 2018. | Finance | Observation | Quarterly | Redwan Sharafuddin |

PROCESS MEASURE DATA COLLECTION

| Change Ideas | Data Source (Where) | Data Collection Method (How) | Time (When) | Responsible Person |
| --- | --- | --- | --- | --- |
| Conduct regular supply chain meetings | Minutes | Review | Monthly | Supply Chain Manager |
| Establish a reliable inventory management system | Inventory Records | Observation | Quarterly | Inventory Manager |
| Foster strong supplier relationships | Supplier Feedback | Survey | Quarterly | Procurement Officer |
| Implement performance monitoring mechanisms | Performance Reports | Review | Monthly | Quality Improvement Team |
| Train staff on effective supply chain practices | Training Records | Observation | After each training | Training Coordinator |

IMPLEMENTATION MONITORING TABLE

| S.No | Change Ideas/Interventions | Number/Session Planned | Number/Session Performed | % | Remark |
| --- | --- | --- | --- | --- | --- |
| 1 | Conduct regular supply chain meetings |  |  |  |  |
| 2 | Establish a reliable inventory management system |  |  |  |  |
| 3 | Foster strong supplier relationships |  |  |  |  |
| 4 | Implement performance monitoring mechanisms |  |  |  |  |
| 5 | Train staff on effective supply chain practices |  |  |  |  |

Do of PDSA Outcome measurement

| Name of QI Project Designed | The aim of this QI project will be aims to reduce supply chain inefficiency from the current median of 17% to <5% from June 21, 2016, to June 20, 2018. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Numerator, Denominator & outcome Indicator | month1 | month2 | month3 | month4 | month5 | month6 | month7 | month8 | month9 | month10 | month11 | month12 | month1 | month2 | month3 | month4 | month5 | month6 |
| Improving Adherence to SCC utilization | (Numerator) Met standards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Denominator) Expected score |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Indicator) Percentage of Met standards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PDSA

Do

- PLAN

- DO

- Test your change ideas one at a time

- Use  Run chart to monitor your QI project over time.

  - Carry out plan

  - Document observations

  - Collect data

  - STUDY

    - Test your change ideas one at a time

    - Use  Run chart to monitor your QI project over time.

    - Carry out plan

    - Document observations

    - Collect data

    - ACT

      - Test your change ideas one at a time

      - Use  Run chart to monitor your QI project over time.

      - Carry out plan

      - Document observations

      - Collect data